## Issues
Item # | Status | Associated Design Entity | Issue Type | Brief Description | Resource | Date identified | Plan date to resolve | Date of last update | Status of resolution / comments
1 | complete | screen | A | Buttons need to appear on screen |  | 2016-04-07 | 2016-04-23 | 2016-04-25 | All buttons appear on screen, buttons now function
2 | complete | database | A | Information needs to be sent to the database |  | 2016-04-07 | 2016-05-23 | 2016-05-25
3 | complete | location services | A | QuirkBoard needs to get the user's location |  | 2016-04-07 | 2016-04-23 | 2016-04-21 | User can refresh location
4 | complete | screen | A | Custom images on buttons |  | 2016-04-07 | 2016-04-16 | 2016-04-14 | All buttons are floating action buttons
5 | complete | database | A | Store location |  | 2016-04-07 | 2016-05-23 | 2016-05-25
6 | complete | screen | A | Custom background/image |  | 2016-04-07 | 2016-04-16 | 2016-04-15 | Background is scrollable
7 | complete | screen | A | Settings Button navigate to settings screen |  | 2016-04-14 | 2016-04-23 | 2016-04-25
8 | complete | screen | A | New Post button create new post |  | 2016-04-14 | 2016-04-23 | 2016-04-25
9 | in progress | screen | A | Home button return to user's location |  | 2016-05-16 | 2016-05-09 | 2016-04-25
10 | complete | screen | I | Combine button and scrolling background code |  | 2016-04-15 | 2016-04-30 | 2016-05-04 | Needs to be resolved before post scrolling/posting can be completed
11 | complete | location services | A | Update user’s location with the push of a button |  | 2016-04-20 | 2016-04-30 | 2016-04-26
12 | in progress | screen | A | Relative post scrolling |  | 2016-04-27 | 2016-05-09 | 2016-04-27
13 | complete | documentation | A | Documentation |  | 2016-04-27 | 2016-05-31 | 2016-05-30
14 | complete | screen | A | Splash screen upon app opening |  | 2016-04-27 | 2016-05-01 | 2016-04-27
15 | complete | screen | A | Character count |  | 2016-04-28 | 2016-05-11 | 2016-05-16
16 | complete | screen | I | Move "send" button for new post to top right |  | 2016-04-28 | 2016-04-28 | 2016-04-28
17 | complete | post | A | Display user entered text on Quirkboard |  | 2016-05-11 | 2016-05-18 | 2016-05-18
18 | complete | post | A | Create new text and image when a user makes a post |  | 2016-05-11 | 2016-05-18 | 2016-05-18
19 | complete | screen | A | Display custom icon for application |  | 2016-05-11 | 2016-05-19 | 2016-05-19
20 | new
21 | new
22 | new
23 | new
24 | new
25 | new
26 | new
27 | new
28 | new
29 | new
30 | new

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete